## ARGOS 2025 tasks
Working on it
Done
It has dependencies
ID | Task |  |  | London | Milan | Frankfurt | Paris | Amsterdam | Deadline | Global Status | Owner | Comments
1 | Load the budget (Monthly budget)
|  | Upload the budget to ARGOS every month | January | Not Started | Not Started | Not Started | Not Started | Not Started | 2025-02-20 | On time
|  |  | February | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | March | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | April | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | May | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | June | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | July | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | August | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | September | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | October | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | November | Not Started | Not Started | Not Started | Not Started | Not Started
|  |  | December | Not Started | Not Started | Not Started | Not Started | Not Started
2 | Acrualls
|  | Accruals |  | working on January files and the design | N. A. | N. A. | N. A. | N. A. | 2025-02-05 | On time

## ARGOS 2024 tasks
Working on it
Done
It has dependencies
ID | Task |  | London | Milan | Frankfurt | Paris | Amsterdam | Deadline | Global Status | Owner | Comments
1 | Summary Closings for 2024
|  | January | Files preapred | Not Started | Files preapred | Files preapred | Files preapred | 2024-12-31 | On time |  | MI just a few differences that will be fixed next year due to taxonomy change, about 12k
|  | February | Files preapred | Not Started | Files preapred | Files preapred | Files preapred | 2024-12-31 | On time
|  | March | Not Started | Not Started | Files preapred | Files preapred | Files preapred | 2024-12-31 | On time
|  | April | Not Started | Files preapred | Files preapred | Files preapred | Files preapred | 2024-12-31 | On time
|  | May | Not Started | Files preapred | Files preapred | Files preapred | Files preapred | 2024-06-12 | Delayed
|  | June | Not Started | Completed | Files preapred | Files preapred | Files preapred | 2024-07-12 | Delayed
|  | July | Not Started | Completed | Completed | Files preapred | Files preapred | 2024-08-12 | Delayed
|  | August | Not Started | Completed | Completed | Files preapred | Completed | 2024-09-12 | Delayed
|  | September | Completed | Completed | Completed | Completed | Completed | 2024-10-12 | Delayed
|  | October | Completed | Completed | Completed | Completed | Completed | 2024-11-12 | Delayed
|  | November | Completed | Completed | Completed | Completed | Completed | 2024-12-12 | Delayed
|  | December | Completed | Completed | Completed | Completed | Completed | 2025-01-12 | Not Started
2 | Remove INCOS from the process
|  | Find out if the geography uses INCOS for conversion, if not, task completed | Completed | Completed | Completed | Completed | Completed | 2024-10-15 | On time |  | FF, PA, Asia and EEUU are using INCOS for the conversion
|  | Know the process they currently use |  |  | Completed | Completed |  | 2024-10-25 | Delayed |  | AM process, starting in January, the only new thing for ARGOS is the taxonomies part, it will replicate them just like how it is doing for INCOS: https://santandernet.sharepoint.com/:x:/r/sites/GlobalServicesCostEuropeTeam/Shared%20Documents/General/4.%20New%20SLB%20%26%20CEB%20GSEC/9.%20Initiatives/9.1%20Argos/Closures%20by%20geographie/Amsterdam%20closures/September/2409_PLANTILLA_INCOS01_AMS_TXT1_ARGOS.xlsx?d=w6f058ade84b84f1da2399c873d1d195e&csf=1&web=1&e=3xqTpf
|  | Have meetings with those responsible to find another way to carry out the conversion without the INCOS |  |  | Cuentas de EQ en SAP: han subido los importes de esas cuentas por Equation para el mes de noviembre, sigue pendiente la creación de las cuentas en SAP | Alinear SAP, delta de los 10 millones localizado: R13 Personnal expense : Difference because M1T1 contain an adjustment, Action Plan : We will request the createion of several GL accounts on SAP and see if they are migrated to ARGOS. GL accounts on SAP that don't migrate to ARGOS, Action Plan : We received informations that we should change the GL accounts. We will do a migration of balance after that the new accounts are created for Paris. Accounting Documents Z0 are not migrated to ARGOS, Issue : We don't know why some amounts are migrated to ARGOS and others are not migrated. |  | 2024-11-01 | Delayed |  | FF and PA process: https://santandernet.sharepoint.com/:b:/r/sites/GlobalServicesCostEuropeTeam/Shared%20Documents/General/4.%20New%20SLB%20%26%20CEB%20GSEC/9.%20Initiatives/9.1%20Argos/Documentation/Formaci%C3%B3n%20Entidades_20240321_vfinl%20(2)%201.pdf?csf=1&web=1&e=bIGNFx
|  | Ensuring that the new way of performing information conversion works |  |  | Not Started | Not Started |  | 2024-11-12 | Delayed
3 | Closing automation
|  | Have a meeting to know the process that they are currently following, the process cannot do the conversion from the INCOS | Completed | N.A. | Waiting for step 2 completed | Waiting for step 2 completed | Completed | 2024-11-15 | Delayed
|  | Make an action plan with a 30/11 deadline to automate the process |  |  | Not Started | Not Started |  | 2024-11-30 | Delayed
4 | Explanatory guide to the closure
|  | Make a guide to geography where the steps to follow for the closure and the explanation of each of them are explained | Completed | N.A. | Waiting for step 3 completed | Waiting for step 3 completed | N.A. | 2024-12-05 | Delayed
5 | Explanation of the closure to the person responsible
|  | Explain the closure to the person who will do it from January 2025 | Completed | N.A. | Waiting for step 4 completed | Waiting for step 4 completed | N.A. | 2024-12-10 | Delayed
6 | Understand the process between ARGOS and MEDEA
|  | Have a meeting with the person in charge of ARGOS to understand what is happening between ARGOS and MEDEA | Completed | Completed | Completed | Completed | Completed | 2024-10-10 | On time |  | https://santandernet.sharepoint.com/:p:/r/sites/GlobalServicesCostEuropeTeam/Shared%20Documents/General/4.%20New%20SLB%20%26%20CEB%20GSEC/9.%20Initiatives/9.1%20Argos/Documentation/ARGOS%20to%20MEDEA.pptx?d=wa5c833f469a84ef09c030da606f57482&csf=1&web=1&e=CUmc2e
7 | Map all files in COSMOS to the output of ARGOS
|  | Have a meeting with the person in charge of ARGOS to know the final date on which we will have all the ARGOS outputs | Completed | N.A. | N.A. | N.A. | N.A. | 2024-10-10 | Delayed |  | We currently have 1 output in ARGOS and 5 in Power BI (a possible number 6)
|  | Have meetings with GSEC team who is currently using COSMOS outputs with Luismi. Make sure they understand the ARGOS outputs and ask for what they need in the face of the disappearance of COSMOS | Completed |  |  |  |  | 2024-10-27 | Delayed
|  | Have meetings with local controllers team who is currently using COSMOS outputs with Luismi. Make sure they understand theARGOS outputs and ask for what they need in the face of the disappearance of COSMOS | Completed |  |  |  |  | 2024-10-27 | Delayed
|  | Map the outputs that our team currently has with those that we will have in ARGOS from now on | Completed |  |  |  |  | 2024-11-15 | Delayed
|  | Ensure that our team will not have problems after January 2025 when COSMOS will disappear | Completed |  |  |  |  | 2024-11-20 | Delayed |  | Proposal for a report made to Luismi, task number 11
|  | Explain to each person in charge what we have done | Completed |  |  |  |  | 2024-11-30 | Delayed
8 | Power BI Pro license and ARGOS
|  | Find out who on our team will need access to ARGOS starting January 2025 and the Power BI Pro license to access the reports | Completed | Not Started | Not Started | Not Started | Not Started | 2024-11-05 | On time |  | España: Sergio Nevado Susana Hernandez Carmen Rivera Londres: Alvaro Redondo Ian Cotta Ben Nixon Alvaro de la Torre
|  | Notify them to request access to ARGOS | Team London did it, still Team Spain pending(to January 2025) | Not Started | Not Started | Not Started | Not Started | 2024-11-20 | Delayed
|  | Notify them to request the PowerBI PRO license | Completed | Not Started | Not Started | Not Started | Not Started | 2024-11-05 | On time
|  | Check that they have access to everything | Team London did it, still Team Spain pending(to January 2025) | Not Started | Not Started | Not Started | Not Started | 2024-11-15 | Delayed
9 | Load the budget
|  | Upload the budget to ARGOS | Completed | Pending, Carmen has to notify us | Pending, Carmen has to notify us | Pending, Carmen has to notify us | Pending, Carmen has to notify us | 2024-12-16 | Delayed
10 | Mochila
|  | Understand the process | Completed | Completed | Completed | Completed | Completed | 2024-11-30 | Delayed
|  | Action plan based on Luismi's meeting | [5 empty] | 2024-11-30 | Delayed
11 | Power BI report requirements
|  | Perfilado para todo el equipo de consulta de Europa ( MPC Spain, Frankfurt, Paris , Milan, Amsterdam, London Branch, Portugal y Polonia) | * Email sent to Luismi, waiting for him. * Luismi is contemplating everything, he will start doing it in January 2025 | N.A. | N.A. | N.A. | N.A. | 2024-12-31 | On time
Jerarquía de Taxonomías ( ahora en los informes tenemos Taxo a nivel 4 ) lo mejor sería que o bien en el detalle de los informes o en el informe dinámico poder ejecutar el output a nivel 0 ó 1 de taxo para no tener tantas líneas en en las descargas y luego tb poder tener mas desglose si se quiere ( ahora en Cosmos en nuestra descarga tenemos en el mismo informe Concepto de coste de nivel 2 a nivel 5 , lo cual te permite agrupar
Informe Real Vs Budget debería de tener las mismas columnas que en el informe de detalle
Informe Dinámico. Debería de poderse incluir el Budget
12 | Load the budget 2024
|  | Upload the budget to ARGOS | Alvaro has to tell us if we will do it or not | N.A. | N.A. | N.A. | N.A. | 2024-12-31 | On time

## ARGOS files London 2024
Pending files to upload on ARGOS
January | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| To upload | To upload | * | To upload | N.A | To upload | N.A | N.A | * | To upload
February | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| To upload | To upload | * | To upload | N.A | To upload | N.A | N.A | * | To upload
March | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
April | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
May | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
June | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
July | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
August | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | To do
September | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | Completed
October | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | Completed | Completed | N.A | Completed | N.A | N.A | Completed | Completed
November | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | Completed | * | Completed | N.A | Completed | N.A | N.A | * | Completed
December | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
[5 empty] | N.A |  | N.A | N.A

## ARGOS files Paris 2024
Pending files to upload on ARGOS
January | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| To upload | N.A | * | To upload | N.A | N.A | N.A | N.A | * | To upload
February | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| To upload | N.A | * | To upload | N.A | N.A | N.A | N.A | * | To upload
March | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
April | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
May | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
June | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
July | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
August | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
September | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
October | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | Completed | Completed | N.A | N.A | N.A | N.A | Completed | Completed
November | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
| Completed | N.A | * | Completed | N.A | N.A | N.A | N.A | * | Completed
December | ARGOS01 | ARGOS02 | ARGOS03 | ARGOS06 | ARGOS10 | POwncosts | PCDistribution | POrchestration | PWDelivery | PBAssignation
|  | N.A |  |  | N.A | N.A | N.A | N.A